## Hoja1
92 to 25k + 180 to 30k
Action | Start Date | Leader | Assistant | Corporate | Cost
Lease out or JV the restaurant to local, regional or national catering/bakery/ | Monday June 8 | John
Operate Gost kitchen after closing | Monday June 8 | Edwin
Hire/partner with catering manager/entrepreneur who wants to open similar operation but needs us a partner to provide location | Monday June 8 | Valentina | Edwin
Hire marketing manager to take over all marketing activities and manage all marketing in the restaurant | Monday June 8 | Valentina/Alexia
Hire catering moms who will help sell catering for us | Monday June 8 | Edwin/John/Valentina
Implement numerous training actions that Alexia created and outlined in September that have never been implemented | Monday June 8 | Edwin/Alexia/Valentina
Hire Supervisor to assist in store with operations to allow GM/DM to generate sales | Monday June 8 | Edwin/Alexia/Valentina/John
Evaluate all costs in restaurant, and determine which ones can be further reduced or eliminated | Monday June 8 | Edwin/Abhi/John/Alexia
Evaluate staff to determine what efficiencies can be gained | Monday January 8 | Edwin
Review Nicks recommendation to determine what to implement | Monday January 8 | John/Edwin
Evaluate other technologies that can be used to gain efficiencies and lower costs | Monday January 8 | Edwin/Alexia
Organized Chariti Event | January 15th | Edwin/John/Valentina
Sales Training
| January 15th | John/Valentina
Weekly Training | January15th | John/Edwin/Valentina/Alexia
Participate/Organize Restaurant Week | January 22th | Edwin
Atend Chember Events | January 22th | Ediwin
Select Store Chariti | January 22th | Edwin/John/Valentina
Organize Greek Happy Hour | January 22th | Edwin/John/Valentina
Organize Nights / Valentine/ e/ Federal Holidays | January 22th | Edwin
Identify and Colaborate with new influencers | January 15th | Alxia/Valentina
Change Catering Pricing | January 15th | Edwin/john/Franky
Increse all Prices / in store and catering | April | Edwin/ John
Create and Promote a Club to get Colombian Coffee and Infussion | January 15th | Valentins
Market Valentines Day | Monday January 8 | Valentina/Edwin
Sell Cookies and Cookie Packages | Monday January 8 | Edwin
Sell Take Home Packages and Baskets | Monday January 8 | Valentina/Edwin
Sell Ship to a Friend Packages | February 1 | Edwin/Valentina /John
Have staff go to Farmers Markets | February 1 | Edwin
Implement Online Marketing Program | Monday January 8 | John/Alexia
Prepare break even analysis | Monday January 8 | Abhi
Prepare six month Preforma | Monday January 8 | Abhi
Prepare Profit Margin on each Menu Item | Monday January 8 | Abhi/Brian/Edwin/Jonh
Local Community Engagement | January 15th
Market by Near by Restaurant |  | Edwin/Alexia
Monday Morning Weekly Calls | Tuesday January 16 | Edwin/John/Valentina/Alexia